WEEK 2 • PROJECT MANAGER INTERNSHIP

DETAILED PROJECT PLAN

AI Production Risk & Operations Assistant

Week 2 planning deliverable based on the approved Week 1 hypothetical software proposal

# PROJECT PLANNING DASHBOARD

| Planning Metric | Baseline | Control Logic |
| --- | --- | --- |
| Project duration | 12 weeks | Fixed planning window; scope is controlled through MVP backlog |
| Delivery framework | Scrum + selected Kanban practices | Two-week Sprints; visible WIP and dependency tracking |
| Core team | 7 role categories | Lean allocation; specialist support is part-time where possible |
| Planned effort | ≈ 2,780 person-hours | Capacity-based planning; includes delivery + QA + PM/product work |
| MVP budget | ₹8.00 lakh | Inherited Week 1 planning ceiling; resource plan must stay within it |
| Primary milestones | Discovery → Prototype → Model → Integrated MVP → UAT → Pilot | Stage gates prevent late surprises |
| Critical path | Data readiness → core application → model → dashboard → UAT → pilot | Reviewed weekly and re-baselined when assumptions change |
| Communication rhythm | Daily team + weekly management + fortnightly stakeholder review | Information tailored to decision-maker needs |

PLAN → EXECUTE → INSPECT → ADAPT → PILOT

# 1. Purpose of the Project Plan

Week 1 established the business case, target customer, software concept, AI approach, indicative budget and 12-week delivery window. Week 2 converts those decisions into an executable management plan. The plan is designed around three evaluation priorities: realism of the schedule, efficient use of resources and effective communication.

The Work Breakdown Structure is treated as the scope baseline from which activities and the schedule are derived. PMI describes a WBS as a deliverable-oriented decomposition of the total project scope and notes its importance for communication, resource allocation and change control. Scrum provides the execution cadence: Sprint Planning, Daily Scrum, Sprint Review and Sprint Retrospective create recurring opportunities for transparency, inspection and adaptation.

# 2. Planning Assumptions & Constraints

| Assumption / Constraint | Planning Treatment | Trigger for Replanning |
| --- | --- | --- |
| 12-week MVP window | Timebox is protected; low-value scope is deferred before quality is reduced. | Critical-path slip > 3 working days |
| Lean team | Use AI-assisted development and automation; specialist roles are part-time where practical. | Sustained capacity shortfall > 15% |
| Customer data may be unavailable initially | Prototype with controlled public/synthetic data; run data-readiness gate before real pilot. | Required fields unavailable or unusable |
| Existing ERP/MES integration is uncertain | Start with CSV/API adapters; treat direct integrations as optional MVP scope. | Integration estimate exceeds planned capacity |
| AI model performance is uncertain | Baseline simple models first; complexity must earn its place through validation. | Model fails predefined validation gate |
| Budget ceiling ₹8L | Track planned vs. actual effort/cost weekly. | Forecast exceeds budget by >10% |
| Human approval is mandatory for consequential recommendations | No autonomous machine control in MVP. | Safety or governance requirement changes |

# 3. Work Breakdown Structure (WBS)

The WBS below is deliverable-oriented and covers the full MVP scope, including project management, data, AI, software, quality, deployment and pilot work.

| WBS ID | Deliverable / Work Package | Key Outputs | Owner |
| --- | --- | --- | --- |
| 1.0 | Project Management & Governance | Charter confirmation, schedule, RAID, change control, reporting | PM |
| 1.1 | Kickoff & alignment | Confirmed goals, stakeholders, working agreements | PM |
| 1.2 | Backlog & scope control | Prioritized Product Backlog, Definition of Done | PM/Product |
| 1.3 | Status, RAID & change control | Weekly dashboard, logs, decisions | PM |
| 2.0 | Discovery & Data Readiness | Validated workflow, data map, acceptance criteria | PM + Product + AI |
| 2.1 | User/workflow validation | User journeys, process map | Product/UX |
| 2.2 | Data audit | Source inventory, quality profile, data dictionary | AI/ML |
| 2.3 | Technical architecture | Architecture, API/data flow, security baseline | Engineer + DevOps |
| 3.0 | UX & Product Design | Wireframes, dashboard prototype, usability feedback | UX |
| 4.0 | Data & Application Foundation | Ingestion, authentication, core order model, APIs | Engineer |
| 4.1 | Data ingestion | CSV/API input, validation, error handling | Engineer + AI |
| 4.2 | Core application | Orders, status, roles, audit trail | Engineer |
| 5.0 | AI Intelligence Layer | Risk model, anomaly detection, evaluation | AI/ML |
| 5.1 | Baseline model | Feature set, baseline, validation pipeline | AI/ML |
| 5.2 | Risk prediction | Delay-risk scoring and thresholding | AI/ML |
| 5.3 | Anomaly detection | Anomaly score and alert logic | AI/ML |
| 5.4 | Explainability | Top-driver explanations and model documentation | AI/ML |
| 6.0 | Decision & Dashboard Layer | Risk dashboard, recommendations, approval flow | Engineer + Product |
| 6.1 | Risk dashboard | Risk heatmap, order detail, filters | Engineer |
| 6.2 | Recommendation layer | Prioritized recommendations + rationale | AI/ML + Product |
| 6.3 | Approval/audit | Human approval, decision history | Engineer |
| 7.0 | Quality, Security & Release | Test evidence, security checks, release candidate | QA + DevOps |
| 7.1 | Functional/integration testing | Test cases, defect log | QA |
| 7.2 | AI validation | Model metrics, false-alert analysis | AI/ML + QA |
| 7.3 | Security/deployment | Access control, logging, deployment | DevOps |
| 8.0 | UAT, Pilot & Closure | Pilot, KPI review, lessons learned, decision | PM + Product |
| 8.1 | UAT | Acceptance results, defect disposition | QA + Product |
| 8.2 | Pilot | User onboarding, usage evidence, feedback | PM/Product |
| 8.3 | Go/Pivot/Stop review | Pilot scorecard and recommendation | Sponsor + PM |

# 4. WBS-to-Work Package Logic

The WBS is not merely a task list. Each work package has an identifiable output and owner. This prevents the common planning error of allocating people to vague activities such as 'work on AI' or 'finish software.' Every package should be small enough to estimate, assign, review and close.

| Package | Definition of Done |
| --- | --- |
| Data readiness | Sources documented, required fields identified, quality issues logged and accepted for the next stage. |
| Core application | Authentication, order/project records and role permissions work against agreed acceptance criteria. |
| Risk model | Baseline and candidate model evaluated on an agreed validation split with documented metrics. |
| Dashboard | User can identify high-risk orders, inspect drivers and view action status. |
| Recommendation | Recommendation is tied to an identified risk driver and requires human approval. |
| Release | Critical defects resolved, security checks completed, deployment repeatable and rollback approach documented. |
| Pilot | Users complete defined scenarios and feedback/KPI evidence is recorded. |

# 5. 12-Week Project Schedule

| Workstream | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PM / governance | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● |
| Discovery & data audit | ● | ● | ○ |  |  |  |  |  |  |  |  |  |
| Architecture / security baseline | ● | ● | ● | ○ |  |  |  |  |  |  |  |  |
| UX / dashboard design | ● | ● | ● | ○ |  |  |  |  |  |  |  |  |
| Data ingestion / application |  | ● | ● | ● | ● | ● | ○ |  |  |  |  |  |
| AI baseline / risk model |  | ● | ● | ● | ● | ● | ● | ○ |  |  |  |  |
| Anomaly / explainability |  |  |  | ● | ● | ● | ● | ● | ○ |  |  |  |
| Dashboard / recommendations |  |  |  |  | ● | ● | ● | ● | ● | ○ |  |  |
| QA / automation |  |  | ○ | ● | ● | ● | ● | ● | ● | ● | ○ |  |
| Security / deployment |  |  |  |  |  | ○ | ● | ● | ● | ● | ○ |  |
| UAT / pilot |  |  |  |  |  |  |  |  |  | ● | ● | ● |
| Go/Pivot/Stop |  |  |  |  |  |  |  |  |  |  |  | ◆ |

Legend: ● active work; ○ setup/handoff/validation; ◆ milestone/decision gate.

# 6. Milestones & Stage Gates

| Milestone | Target | Entry / Exit Criteria | Decision Owner |
| --- | --- | --- | --- |
| M1: Project kickoff | End W1 | Scope, roles, cadence and backlog agreed | Sponsor + PM |
| M2: Discovery/data gate | End W2 | Problem workflow, data path and MVP acceptance criteria confirmed | Product + PM |
| M3: Architecture/design gate | End W3 | Architecture, UX direction and security baseline accepted | Product + Engineering |
| M4: Core foundation | End W4 | Data ingestion and core application skeleton operational | Engineering |
| M5: Model baseline | End W6 | Baseline model and evaluation pipeline working | AI/ML + Product |
| M6: Integrated MVP | End W9 | Risk, dashboard and recommendation workflow integrated | PM + Product |
| M7: Release candidate | End W10 | Critical quality/security gates passed | QA + DevOps |
| M8: UAT complete | End W11 | Acceptance scenarios passed or formally deferred | Product |
| M9: Pilot & decision | End W12 | Pilot evidence reviewed; Go/Pivot/Stop decision recorded | Sponsor |

# 7. Resource Allocation & Capacity Model

Resource allocation is based on the principle that not every role needs to be full-time for 12 weeks. Full-time capacity is protected for work that can block the critical path; design, product, DevOps and QA support are deliberately scaled around their peak workload.

| Role | Planned allocation | Approx. hours | Peak period | Why this allocation |
| --- | --- | --- | --- | --- |
| Project Manager / Product Lead | 100% × 12 weeks | 480 | All weeks | Continuous coordination, scope, risks and decisions |
| Product Owner / Manufacturing SME | 40% × 12 weeks | 192 | W1-W3, W8-W12 | Requirements, domain validation, acceptance |
| Full-stack Engineer | 100% × 12 weeks | 480 | W3-W10 | Core application and dashboard critical path |
| AI/ML Engineer | 100% × 12 weeks | 480 | W2-W10 | Data, modeling, evaluation and monitoring |
| UX/UI Designer | 50% × 6 weeks | 120 | W1-W6 | High concentration early; light support later |
| QA / Automation | 60% × 8 weeks | 192 | W4-W12 | Testing rises as features stabilize |
| DevOps / Security | 25% × 8 weeks | 80 | W3-W12 | Architecture, environments, security and release |
| Total planned effort |  | 2,024 |  | Indicative productive effort before contingency |

Capacity note: 2,024 hours is a planning estimate, not a claim about employee working hours. It assumes 40 hours/week as nominal full-time capacity and deliberately does not load every person to 100% throughout the project.

# 8. Resource Efficiency Rules

Protect the AI/ML and full-stack engineers from unnecessary meetings during critical build blocks.

Use the Product Owner/Manufacturing SME heavily during discovery and acceptance, not as a full-time development resource.

Concentrate UX work before the main build, with targeted usability support later.

Increase QA involvement as integrated functionality accumulates rather than waiting until the final week.

Bring DevOps/security in before release so deployment and access-control issues do not become late-stage blockers.

Use AI coding/testing/documentation tools as accelerators, while keeping human review and accountability for production changes.

If capacity falls, reduce low-priority backlog scope before increasing overtime or compromising quality gates.

# 9. Critical Path & Dependencies

| Dependency Chain | Why it matters | Management Action |
| --- | --- | --- |
| Data readiness → model development | AI model cannot be validated without usable features/labels. | Complete data audit by W2; maintain fallback prototype dataset. |
| Architecture → application foundation | Core data/API choices affect downstream work. | Architecture decision record by W3. |
| Application + model → dashboard | Dashboard needs stable risk outputs and user workflows. | Integrate through a defined API contract. |
| Integrated MVP → QA/UAT | Testing meaningful only when the major workflow is stable. | Feature freeze for release candidate. |
| UAT → pilot → Go/Pivot/Stop | Pilot decision depends on accepted product and measured evidence. | Predefine gate criteria before UAT. |

The schedule intentionally contains parallel work where dependencies permit it. For example, UX and data preparation can progress while architecture is finalized. This reduces total duration without pretending that dependent activities can be performed simultaneously.

# 10. Communication Management Plan

The communication plan follows a simple principle: communicate the level of detail required by the receiver's decision responsibility. PMI guidance on project communication emphasizes identifying who needs what information, when it is needed and how it should be delivered, and notes that senior stakeholders generally need summarized information rather than task-level detail.

| Audience | Information | Format / Channel | Frequency | Owner | Response expectation |
| --- | --- | --- | --- | --- | --- |
| Development + AI/ML team | Sprint goal, blockers, dependencies, decisions | Daily Scrum + team board | Daily | PM / Scrum Master | Blockers surfaced same day |
| Product Owner | Backlog, acceptance questions, product trade-offs | Backlog review / chat | 2-3× weekly | PM | Decision within 1 business day |
| Executive Sponsor | Milestones, budget forecast, top risks, decisions needed | 1-page dashboard / meeting | Weekly | PM | Escalation/approval within 2 business days |
| Stakeholder group | Working increment, feedback, scope changes | Sprint Review | Every 2 weeks | Product Owner | Feedback within review window |
| QA + DevOps | Release scope, defects, security findings | Issue tracker + release review | Weekly / release-based | Engineering lead | Critical issues immediately |
| Pilot users | Onboarding, known limitations, feedback requests | Demo + user channel | At pilot milestones | Product / PM | Feedback within agreed pilot window |

# 11. Communication Escalation Matrix

| Situation | First action | Escalation level | Target response |
| --- | --- | --- | --- |
| Task blocked < 1 day | Team resolves in Daily Scrum | None | Same day |
| Dependency blocked 1-2 days | PM coordinates owner | Functional lead | Within 1 business day |
| Critical-path delay > 3 days | PM reforecast + propose recovery | Sponsor/Product Owner | Within 2 business days |
| Budget forecast > 10% over plan | PM submits impact/options | Sponsor | Within 2 business days |
| Critical security defect | Stop affected release activity | Sponsor + Security/DevOps | Immediate |
| AI model below gate | Return to model/data work; reassess scope | Product + Sponsor if milestone affected | Within 1 business day |
| Material scope change | Impact analysis before work begins | Product Owner + Sponsor | Within 2 business days |

# 12. Meeting Cadence & Timeboxing

| Event | Duration | Participants | Purpose | Output |
| --- | --- | --- | --- | --- |
| Daily Scrum | 15 min | Developers; PM facilitates as needed | Inspect progress and surface impediments | Updated short-term plan |
| Backlog refinement | 45-60 min | PM/Product + relevant specialists | Clarify and size upcoming work | Ready backlog items |
| Sprint Planning | Up to 2 hours for 2-week sprint | Scrum Team | Set Sprint Goal and forecast work | Sprint Backlog |
| Sprint Review | 60-90 min | Team + stakeholders | Inspect increment and collect feedback | Updated priorities |
| Sprint Retrospective | 45-60 min | Scrum Team | Improve ways of working | 1-3 improvement actions |
| Weekly PM review | 30 min | PM + Product + functional leads | Budget, schedule, RAID and decisions | Executive dashboard / actions |

The official Scrum Guide sets a maximum Sprint length of one month; two-week Sprints are a common practical cadence and are used here to create rapid feedback. Scrum events are designed around transparency, inspection and adaptation.

# 13. Reporting Dashboard

| Dashboard Area | Weekly Metric | Decision Trigger |
| --- | --- | --- |
| Schedule | Milestones planned vs. actual | Critical milestone variance > 3 days |
| Scope | Committed vs. completed backlog; change count | Material scope change or throughput decline |
| Budget | Planned vs. actual/forecast spend | Forecast >10% above ceiling |
| Quality | Open defects by severity | Any critical defect blocks release |
| AI | Validation metrics + false-alert trend | Below predefined model gate |
| Data | Completeness/freshness exceptions | Required fields below agreed threshold |
| Risk | Top 5 risks + exposure | High-risk item without owner/mitigation |
| People | Capacity vs. planned load | Sustained overload or bottleneck |
| Stakeholders | Decisions pending | Decision exceeds response target |

# 14. Change Control & Scope Protection

A change is not rejected automatically; it is assessed. Every material change must state the business reason, effort, schedule impact, dependency impact, risk impact and whether another item should be removed. This protects the 12-week timebox while allowing evidence-driven adaptation.

| Change Type | Example | Default Action |
| --- | --- | --- |
| Must-have correction | Security defect or broken acceptance criterion | Prioritize immediately |
| Customer-validated value | Pilot evidence shows a missing essential workflow | Assess and trade against existing scope |
| Nice-to-have | Additional visualization | Backlog for post-MVP |
| Strategic change | New target market or business model | Sponsor decision; may trigger re-planning |

# 15. Project Manager Control Rhythm

Every day: blockers, dependencies, critical decisions.

Every week: schedule, budget, RAID, capacity, stakeholder decisions.

Every two weeks: working increment, feedback, retrospective, backlog adaptation.

At gates: evidence-based Go/Pivot/Stop decision.

# 16. Why This Plan Is Realistic

The plan uses a fixed MVP scope rather than attempting to build an ERP replacement.

Two-week iterations provide repeated opportunities to discover problems before the final week.

Data readiness is brought into Week 1-2 rather than assuming perfect data will appear later.

AI work begins with a baseline model instead of assuming an advanced model is automatically better.

UX, QA and DevOps capacity is concentrated around their actual peaks rather than assigning every role full-time.

Critical-path dependencies are explicitly tracked, and schedule recovery is achieved first through scope trade-offs rather than uncontrolled overtime.

Communication is role-specific: executives receive decisions and variances; the team receives blockers and technical detail.

The pilot is treated as a decision gate, not as proof that the software will succeed.

# 17. Week 2 Deliverable Summary

| Required Internship Element | Where Addressed |
| --- | --- |
| Work Breakdown Structure | Section 3 + WBS work packages |
| Project Schedule | Section 5 + milestones + critical path |
| Resource Allocation | Section 7 + efficiency rules |
| Communication Plan | Section 10 + escalation matrix |
| Realistic deadlines | 12-week schedule with dependencies and gates |
| Efficient resource use | Peak-based allocation and capacity assumptions |
| Effective communication | Audience-specific cadence, channel, owner and response expectations |
| Project controls | RAID, dashboard, change control and gate reviews |

# 18. References

Scrum Guides, The 2020 Scrum Guide, Ken Schwaber & Jeff Sutherland. https://scrumguides.org/scrum-guide.html

Scrum.org, Introduction to the Sprint and Scrum Events. https://www.scrum.org/resources/introduction-sprint

Project Management Institute (PMI), Work Breakdown Structure: Basic Principles. https://www.pmi.org/learning/library/work-breakdown-structure-basic-principles-4883

Project Management Institute (PMI), Developing and elaborating effective work breakdown structures. https://www.pmi.org/learning/library/developing-elaborating-work-breakdown-structures-7241

Project Management Institute (PMI), Project communication – foundation for project success. https://www.pmi.org/learning/library/2019/04/07/15/37/project-communication-foundation-project-success-7796

# 19. Planning Caveat

This is a hypothetical project plan. Hours, cost ceiling, milestone dates and resource allocations are planning assumptions derived from the Week 1 proposal, not commitments from named employees or vendors. The first two weeks of execution should be used to replace assumptions with actual capacity, customer data availability and technical estimates. The Project Manager should formally re-baseline the schedule if evidence materially changes the original assumptions.

END OF WEEK 2 PROJECT PLAN