WEEK 3 • PROJECT MANAGER INTERNSHIP

PROJECT EXECUTION PLAN

AI Production Risk & Operations Assistant

Week 3 execution, quality, change, communication and project-control framework

# EXECUTION CONTROL DASHBOARD

| Control Area | Target State | Trigger / Escalation |
| --- | --- | --- |
| Scope | MVP backlog remains controlled | Material change requires impact assessment |
| Schedule | 12-week timebox protected | Critical-path variance >3 working days |
| Quality | Every released increment meets Definition of Done | Critical defect or failed acceptance criterion blocks release |
| AI quality | Model evaluated against predefined metrics and baseline | Below gate → investigate, retrain, simplify or stop |
| Budget | ₹8.00L planning ceiling | Forecast >10% above ceiling |
| Risk | Top risks owned and actively mitigated | High risk without mitigation owner |
| Communication | Decision-relevant information reaches each stakeholder | Decision overdue beyond agreed SLA |
| Change | Evidence-driven adaptation without uncontrolled scope growth | Unapproved scope or requirement enters delivery |

EXECUTE → MEASURE → INSPECT → CONTROL → ADAPT → DELIVER

# 1. Purpose & Execution Philosophy

This plan converts the Week 2 project plan into an operating system for the 12-week MVP. It defines how the Project Manager will control scope, schedule, cost, quality, AI performance, risks, changes and stakeholder communication while enabling the team to deliver incrementally.

The execution approach uses Scrum as the primary delivery framework with two-week Sprints. Scrum emphasizes transparency, inspection and adaptation; the Sprint Review is intended as a collaborative working session where the team and stakeholders inspect the Increment and adapt future plans, while the Sprint Retrospective focuses on improving quality and effectiveness. citeturn0search11turn0search8

# 2. Execution Governance Model

| Layer | Primary Question | Owner | Evidence / Artifact |
| --- | --- | --- | --- |
| Business | Are we still solving the right problem? | Sponsor + Product Owner | Product Goal, KPI dashboard, gate decisions |
| Product | Are we building the highest-value MVP? | Product Owner | Product Backlog, acceptance criteria |
| Delivery | Are we on track? | Project Manager / Scrum Master | Sprint Backlog, schedule, RAID, status report |
| Engineering | Is the solution technically sound? | Engineering Lead | Architecture records, code review, CI/CD |
| AI | Is the model reliable and appropriate? | AI/ML Engineer | Validation report, model card, monitoring |
| Quality | Is the Increment releasable? | QA + Developers | Test evidence, defects, Definition of Done |
| Security | Is risk acceptable? | DevOps/Security | Security checks, access review, logs |
| Stakeholders | Are decisions timely? | PM | Decision log, communication dashboard |

# 3. Quality Management Plan

Quality is built into every Sprint rather than postponed to the end. Scrum's Definition of Done provides a shared quality standard for an Increment; an item that does not meet the Definition of Done is not considered Done. citeturn0search0turn0search1

## 3.1 Definition of Done

Acceptance criteria are met and demonstrated.

Code is peer-reviewed and merged through the agreed repository workflow.

Automated tests relevant to the change pass.

Integration/regression testing for affected workflows is complete.

No unresolved critical defect remains.

Security checks relevant to the change are completed.

Logging and error handling are implemented where required.

User-facing documentation or release notes are updated where needed.

AI-related changes have documented evaluation results and known limitations.

Deployment/release checklist is complete.

## 3.2 Quality gates by lifecycle stage

| Stage | Quality Check | Pass Criteria | Action if Failed |
| --- | --- | --- | --- |
| Requirements | Acceptance criteria review | Clear, testable, non-conflicting | Return to Product Owner |
| Design | UX + architecture review | Meets user workflow and technical constraints | Revise before build |
| Development | Code review + automated tests | Required checks pass | Fix before merge |
| AI modeling | Validation + baseline comparison | Predefined metric gate met or justified | Retrain/simplify/reassess |
| Integration | End-to-end testing | Core workflow works across components | Defect correction |
| Security | Access/configuration checks | No unresolved critical finding | Block release |
| UAT | User acceptance scenarios | Critical scenarios accepted | Fix/defer formally |
| Pilot | Outcome + usability review | Evidence supports next decision | Go/Pivot/Stop |

## 3.3 Defect management

| Severity | Definition | Response | Release Rule |
| --- | --- | --- | --- |
| Critical | Security, data-loss, system-blocking or unsafe outcome | Immediate owner + escalation | Blocks release |
| High | Major workflow materially impaired | Fix in current Sprint where feasible | Normally blocks release |
| Medium | Workaround exists; meaningful degradation | Prioritize by impact | May release with approval |
| Low | Minor cosmetic/usability issue | Backlog | Does not normally block |

# 4. AI-Specific Quality Management

AI quality cannot be reduced to a single accuracy number. The project will evaluate the model against the business problem, the cost of false positives/negatives, data quality, calibration where probabilities are displayed, and user usefulness.

| AI Control | What We Measure | Execution Rule |
| --- | --- | --- |
| Baseline comparison | Simple baseline vs candidate model | Complex model must show material benefit before adoption |
| Precision | Share of predicted high-risk cases that are actually high-risk | Track false-alert burden |
| Recall | Share of actual high-risk cases identified | Prioritize carefully because missed risks can be costly |
| F1 | Balance of precision and recall | Use alongside business impact |
| Calibration | Whether predicted probabilities correspond to observed frequencies | Required if risk probability is shown |
| Data drift | Changes in feature distributions | Monitor post-pilot |
| Recommendation quality | User acceptance/usefulness of recommended actions | Human review required |
| Explainability | Whether main drivers are understandable and consistent | No opaque recommendation for consequential decisions |

NIST's AI RMF is designed to help organizations manage AI risks throughout design, development, deployment and evaluation, with trustworthiness characteristics including validity/reliability, safety, security/resilience, accountability/transparency, explainability, privacy and fairness. citeturn0search6turn0search13

# 5. Test Strategy

| Test Layer | Examples | Owner | Timing |
| --- | --- | --- | --- |
| Unit testing | Functions, transformations, validation rules | Developers | Continuous |
| API/integration | Data ingestion, model API, dashboard API | Developers + QA | Each Sprint |
| UI testing | Login, filters, risk drill-down, approval flow | QA | Each Sprint |
| Regression | Core workflows after changes | QA | Each Sprint/release |
| Performance | Dashboard/API response and data-processing workload | QA + DevOps | W9-W10 |
| Security | Authentication, authorization, configuration, dependency checks | DevOps/Security | W3 onward; release gate |
| AI validation | Time-based/holdout evaluation, false-alert analysis | AI/ML + QA | W5-W10 |
| UAT | Realistic production-risk scenarios | Product + Pilot users | W11 |
| Pilot monitoring | Usage, errors, model alerts, user feedback | PM + Product + Engineering | W12+ |

# 6. Change Management Plan

Change is expected in an adaptive project. The goal is not to prevent change; it is to ensure that changes are intentional, evaluated and visible. Scrum itself expects the Product Backlog to adapt based on inspection and changing circumstances. citeturn0search8turn0search11

| Step | Action | Owner | Output |
| --- | --- | --- | --- |
| 1. Capture | Record request, source and business reason | PM/Product | Change request |
| 2. Classify | Defect, compliance/security, customer value, enhancement or strategic change | PM | Change category |
| 3. Impact assess | Estimate effort, schedule, budget, dependencies, quality and AI risk | Relevant leads | Impact assessment |
| 4. Decide | Accept, defer, reject or trade against existing scope | Product Owner / Sponsor as appropriate | Decision |
| 5. Update | Update backlog, schedule, RAID and budget forecast | PM/Product | Controlled baseline |
| 6. Communicate | Tell affected stakeholders what changed and why | PM | Decision record |
| 7. Verify | Check that implementation matches approved change | QA/Product | Acceptance evidence |

## 6.1 Change decision matrix

| Change Type | Example | Default Decision Logic |
| --- | --- | --- |
| Critical defect/security | Access-control vulnerability | Immediate priority; may interrupt Sprint |
| Regulatory/safety requirement | Required control discovered | Assess immediately; release may pause |
| Validated customer need | Pilot users repeatedly request essential workflow | Consider through Product Backlog and scope trade-off |
| Efficiency improvement | Automation saves significant recurring effort | Accept if low-risk and capacity allows |
| Nice-to-have | Extra dashboard chart | Defer unless replacing lower-value scope |
| Strategic pivot | Target customer/problem changes | Sponsor gate; re-baseline project if approved |

# 7. Progress Monitoring & Control

The Project Manager will operate a weekly control loop across scope, schedule, cost, quality, risk, AI performance, people and stakeholder decisions.

| Control Area | Metric | Green | Amber | Red |
| --- | --- | --- | --- | --- |
| Schedule | Critical-path variance | ≤1 day | 2-3 days | >3 days |
| Budget | Forecast vs ₹8L ceiling | ≤5% | 5-10% | >10% |
| Scope | Unapproved scope items | 0 | 1 | ≥2 |
| Quality | Critical defects | 0 | 0 with immediate fix | ≥1 unresolved |
| AI | Model gate | Meets target | Within agreed tolerance | Fails gate |
| Risk | High risks without active mitigation | 0 | 1 | ≥2 |
| Capacity | Sustained overload | <10% | 10-15% | >15% |
| Decisions | Overdue critical decisions | 0 | 1 | ≥2 |

## 7.1 Weekly project-control dashboard

| Dashboard Block | Weekly Questions | Action |
| --- | --- | --- |
| Scope | What changed? What is completed? What is at risk? | Reprioritize backlog |
| Schedule | Are critical-path tasks slipping? | Recovery plan or scope trade-off |
| Budget | Are actual/forecast costs within ceiling? | Control spend or escalate |
| Quality | Are defects trending down? | Increase QA/fix capacity |
| AI | Is the model improving and trustworthy? | Tune, retrain, simplify or stop |
| Risk | What could hurt delivery next? | Owner + mitigation + due date |
| People | Where is capacity constrained? | Reallocate or reduce WIP |
| Stakeholders | What decision is blocking progress? | Escalate with options |

# 8. Earned Value / Schedule Variance Lite

For a short 12-week hypothetical project, full enterprise EVM can add unnecessary complexity. We will use a lightweight planned-vs-earned approach to identify early schedule problems.

| Metric | Formula | Interpretation |
| --- | --- | --- |
| Planned % | Budgeted work planned by status date ÷ total planned work | How much work should be complete |
| Earned % | Accepted work completed ÷ total planned work | How much value is actually complete |
| Schedule variance (pp) | Earned % − Planned % | Negative value indicates schedule underperformance |
| Cost variance (₹) | Budgeted value of accepted work − actual cost | Negative value indicates overspend |

Example: by the end of Week 6, if 55% of planned work should be complete but only 48% has been accepted, schedule variance is 48% − 55% = −7 percentage points. The PM then investigates the critical path rather than simply declaring the project '7% late.'

# 9. Communication & Progress Reporting

| Audience | Message | Format | Cadence | Escalation |
| --- | --- | --- | --- | --- |
| Team | Blockers, priorities, dependencies | Daily Scrum + board | Daily | Immediate for critical blockers |
| Product Owner | Backlog, product decisions, acceptance | Backlog/decision review | 2-3× weekly | 1 business day |
| Sponsor | Overall status, budget, risks, decisions | Executive dashboard | Weekly | 2 business days |
| Stakeholders | Increment, feedback, environment changes | Sprint Review | Biweekly | At review |
| QA/Security | Defects, quality risks, release scope | Issue/release review | Weekly | Immediate critical issue |
| Pilot users | Known limitations, changes, feedback | Demo/user channel | At pilot milestones | Same business day for severe issue |

## 9.1 Executive status format

| Section | Content |
| --- | --- |
| Overall RAG | Green / Amber / Red with one-sentence reason |
| Accomplished | 3-5 highest-value completed outcomes |
| Next | 3-5 most important upcoming outcomes |
| Schedule | Milestone status + critical-path variance |
| Budget | Actual + forecast vs ceiling |
| Top risks | Top 3 risks, exposure and mitigation |
| Decisions required | Decision, owner, deadline, recommended option |
| AI quality | Current validation status and key caveat |

# 10. Escalation & Decision Management

The PM acts as a shock absorber: issues are not hidden from leadership, but they are packaged with context, options and a recommendation so executives can make decisions quickly.

| Trigger | PM Action | Escalate To | Target |
| --- | --- | --- | --- |
| Critical-path delay >3 days | Reforecast + recovery options | Sponsor/Product | 2 business days |
| Budget forecast >10% | Show cause + alternatives | Sponsor | 2 business days |
| Critical security issue | Pause affected release path | Sponsor + Security | Immediate |
| AI gate failure | Compare model, data and scope options | Product + Sponsor if milestone impacted | 1 business day |
| Major scope request | Impact analysis before commitment | Product/Sponsor | 2 business days |
| Team capacity bottleneck | Reallocate, reduce WIP or scope | PM + Functional lead | 1 business day |

# 11. RAID Integration During Execution

| Log | Minimum Fields | Review |
| --- | --- | --- |
| Risks | Description, probability, impact, score, owner, mitigation, due date | Weekly |
| Assumptions | Assumption, evidence status, owner, validation date | Weekly / at gates |
| Issues | Problem, impact, owner, target resolution, escalation | Daily/weekly |
| Dependencies | Upstream item, downstream impact, owner, required date, status | Daily for critical dependencies |

# 12. Execution Artifacts & Evidence

Product Backlog and Sprint Backlog

Definition of Done and acceptance criteria

Architecture Decision Records

Data dictionary and data-quality reports

Model evaluation report and model/version record

Test cases and defect log

Security checklist and release checklist

RAID Log and Change Log

Decision Log

Weekly executive dashboard

Sprint Review feedback

Retrospective improvement actions

UAT sign-off/evidence

Pilot KPI report and Go/Pivot/Stop decision

# 13. Project Control Calendar

| Cadence | Control Activity | Primary Output |
| --- | --- | --- |
| Daily | Daily Scrum; blocker/dependency updates | Updated execution plan |
| Twice weekly | Backlog refinement / product decision touchpoint | Ready backlog + decisions |
| Weekly | PM control review; RAID; budget; schedule; quality; AI dashboard | Executive status report |
| Every 2 weeks | Sprint Review + Retrospective | Feedback + improvement actions |
| At each gate | Evidence review | Go / Pivot / Hold / Stop decision |
| Before release | Quality + security + AI readiness review | Release decision |
| Post-pilot | Outcome review | Scale / pivot / stop recommendation |

# 14. Keeping the Project on Track: Recovery Playbook

| Problem | First Response | Second Response | Last Resort |
| --- | --- | --- | --- |
| Schedule slip | Identify critical-path cause | Reallocate capacity / reduce WIP | Trade scope; do not automatically add overtime |
| Budget pressure | Check burn + cause | Remove low-value work / renegotiate tool usage | Re-baseline with sponsor |
| Quality decline | Stop adding new work to affected area | Increase test/fix capacity | Delay release |
| Model underperforms | Review data + baseline | Simplify model / adjust features | Remove AI feature from MVP and use rules/analytics |
| Stakeholder delay | Escalate decision with options | Sponsor decision | Re-plan dependent work |
| Integration failure | Use adapter/manual import for MVP | Replace integration approach | Defer integration from MVP |

# 15. Execution Principles

Make progress visible; hidden work becomes hidden risk.

Protect the Product Goal, not every original feature.

Never trade away critical quality or security to preserve a cosmetic deadline.

Use the simplest technical solution that satisfies the validated requirement.

Treat AI as a probabilistic component that requires measurement and monitoring.

Escalate with options and recommendations, not only problems.

Use stakeholder feedback to adapt the backlog, not to create uncontrolled scope.

Document decisions so the team does not repeatedly solve the same disagreement.

Use retrospectives to improve the process, not to assign blame.

# 16. Week 3 Evaluation Alignment

| Internship Criterion | How This Plan Addresses It |
| --- | --- |
| Comprehensiveness | Covers quality, change, communication, progress control, AI quality, risks, defects, governance and recovery. |
| Appropriate procedures | Uses Scrum events, Definition of Done, quality gates, risk-based escalation and AI lifecycle controls. |
| Keeping project on track | Defines measurable RAG thresholds, weekly dashboard, critical-path triggers, change control and recovery playbook. |
| Quality management | Definition of Done, test layers, defect severity, AI evaluation and release gates. |
| Change management | Capture → assess → decide → update → communicate → verify workflow. |
| Communication strategy | Role-specific information, cadence, channel, owner and escalation expectations. |

# 17. Final Execution Recommendation

The project should be executed as an evidence-driven, two-week Sprint cycle with continuous quality control. The Project Manager should preserve the 12-week timebox by controlling WIP and scope, not by sacrificing quality. Each Sprint should produce an inspectable Increment that meets the Definition of Done, and stakeholder feedback should influence future backlog priorities. For AI components, the team should continuously evaluate whether the AI is actually the appropriate solution and whether its risks remain acceptable.

NIST's AI RMF explicitly notes that AI systems may not always be the right solution for a task and recommends ongoing assessment of benefits, risks and trade-offs. That principle is incorporated into this plan through model gates, fallback rules and the option to remove an AI feature from the MVP if it does not outperform a simpler approach. citeturn0search15

# 18. References

The Scrum Guide, 2020, Ken Schwaber & Jeff Sutherland. https://scrumguides.org/scrum-guide.html

Scrum.org, What is the Definition of Done? https://www.scrum.org/resources/what-definition-done-0

Scrum.org, Conducting the Sprint Review. https://www.scrum.org/resources/conducting-sprint-review

NIST, Artificial Intelligence Risk Management Framework (AI RMF 1.0). https://www.nist.gov/publications/artificial-intelligence-risk-management-framework-ai-rmf-10

NIST AI RMF Playbook, Manage Function. https://airc.nist.gov/airmf-resources/playbook/manage/

Project Management Institute, Project communication management – five steps. https://www.pmi.org/learning/library/2019/04/07/15/17/project-communication-management-five-steps-5115

# 19. Planning & Evidence Caveat

This is a hypothetical execution plan. Thresholds, hours, budget triggers and response times are management planning assumptions unless explicitly identified as external standards. During real execution, baseline values would be approved by the sponsor/product owner and updated when actual data, capacity and pilot evidence become available.

END OF WEEK 3 PROJECT EXECUTION PLAN